## Intro
Sistema Home Banking
Report Scrum

Principi di Progettazione del Software a.a. 2018-2019
Università del Salento - Facoltà di Ingegneria dell’Informazione

Mirko Zizzari

## Product Backlog
		Nuove stime allo Sprint…
Voce	Stima iniziale dimensioni / (Story points)	1	2	3	4			Effort Totale	Sprint 1	Sprint 2	Sprint 3	Sprint 4
Definire I requisiti e / l’architettura di alto livello (attori e casi d’uso)	20	5	0	0	0		Stimato	320	257	135	45	4
Definire I requisiti di sistema	5	0	0	0	0		Ideale	320	240	160	80	0
Progettazione del database	20	5	0	0	0
Configurazione Ambiente di Lavoro	10	2	0	0	0
Gestione Accessi	20	20	10	0	0
Testing	20	20	15	10	2
Come amministratore voglio / Creare il profilo delle banche del territorio	15	15	7	3	0
Come amministratore voglio / Definire le credenziali di un direttore per ogni banca	15	15	7	0	0
Come direttore voglio / Creare una o più filiali della mia banca	15	15	7	0	0
Come direttore voglio / Definire le credenziali dei cassieri per ogni filiale	15	15	7	0	0
Come direttore voglio / Creare un catalogo di / prodotti (conto corrente, carta prepagata) / e servizi (ricarica cellulare, pagamento bollo auto)	20	20	10	0	0
Il sistema applica periodicamente / gli interessi sui prodotti (conto e carta prepagata) / Con una percentuale definita dal direttore di banca. / Rispettando gli automatismi per operazioni dispositive	10	10	10	10	0
Come cassiere voglio / Prendere visione delle operazioni dei clienti / Potendole filtrare ed esportare	25	25	13	5	0
Come cassiere devo / Autorizzare o negare le operazioni dispositive	20	20	10	5	0
Come cliente della filiale voglio / Eseguire operazioni informative	15	15	7	3	0
Come cliente della filiale voglio / Eseguire operazioni dispositive	15	15	10	5	0
Come cliente voglio / Usufrire dei servizi offerti / (ricariche cellulare, pagamento bollo auto)	20	20	10	2	0
Un utente generico può / Prendere visione dei servizi offerti dal sistema, / Delle banche, ecc.	10	10	5	0	0
Un utente generico può / Richiedere la registrazione all’amministratore / Specificando banca e filiale	10	10	7	2	2
Documentazione	20	10	10	10	2

## Github Issues
Group	State	Repo Name	Issue Number	Issue Title	Pipeline	Story Points	Milestone	Labels
Completed	closed	homebanking-demo	4	Create MySQL Tables	Not Available	3	Sprint 1	Sprint 1,backend,enhancement
Completed	closed	homebanking-demo	1	requirements and use cases	Not Available	13	Sprint 1	Sprint 1,enhancement
Completed	closed	homebanking-demo	2	Database design	Not Available	13	Sprint 1	Sprint 1,enhancement
Completed	closed	homebanking-demo	3	configurations for environment and builds	Not Available	5	Sprint 1	Sprint 1,enhancement
Completed	closed	homebanking-demo	6	BankManager dashboard	Not Available	13	Sprint 2	Sprint 2,backend
Completed	closed	homebanking-demo	7	employee dashboard	Not Available	21	Sprint 2	Sprint 2,backend
Completed	closed	homebanking-demo	8	customer dashboard	Not Available	21	Sprint 2	Sprint 2,backend
Completed	closed	homebanking-demo	9	visitor	Not Available	13	Sprint 2	Sprint 2,backend
Completed	closed	homebanking-demo	15	upload images	Not Available	8	Sprint 2	Sprint 2,backend
Completed	closed	homebanking-demo	16	export in pdf	Not Available	8	Sprint 2	Sprint 2,backend
Completed	closed	homebanking-demo	17	retrieve images	Not Available	5	Sprint 2	Sprint 2,backend
Completed	closed	homebanking-demo	5	Admin Dashboard	Not Available	13	Sprint 2	Sprint 2,backend,enhancement
Completed	closed	homebanking-demo	10	implement spring security	Not Available	13	Sprint 2	Sprint 2,backend,enhancement,security
Completed	closed	homebanking-demo	11	retrieve users info for web services	Not Available	8	Sprint 2	Sprint 2,backend,enhancement,security
Completed	closed	homebanking-demo	14	operation filters	Not Available	21	Sprint 2	Sprint 2,backend,jpa
Completed	closed	homebanking-demo	21	create bank	Not Available	5	Sprint 3	Sprint 3,administration,frontend
Completed	closed	homebanking-demo	22	authorize registration request	Not Available	5	Sprint 3	Sprint 3,administration,frontend
Completed	closed	homebanking-demo	27	automation of interests rate on products	Not Available	8	Sprint 3	Sprint 3,backend,business
Completed	closed	homebanking-demo	18	login	Not Available	8	Sprint 3	Sprint 3,backend,frontend
Completed	closed	homebanking-demo	30	deposit operation	Not Available	5	Sprint 3	Sprint 3,customer,frontend
Completed	closed	homebanking-demo	31	withdraw operation	Not Available	5	Sprint 3	Sprint 3,customer,frontend
Completed	closed	homebanking-demo	32	refill operation	Not Available	5	Sprint 3	Sprint 3,customer,frontend
Completed	closed	homebanking-demo	33	transfer operation	Not Available	8	Sprint 3	Sprint 3,customer,frontend
Completed	closed	homebanking-demo	34	car tax	Not Available	5	Sprint 3	Sprint 3,customer,frontend
Completed	closed	homebanking-demo	35	customer list operation	Not Available	5	Sprint 3	Sprint 3,customer,frontend
Completed	closed	homebanking-demo	36	employee list operations	Not Available	8	Sprint 3	Sprint 3,employee,frontend
Completed	closed	homebanking-demo	19	home page with banks informations	Not Available	5	Sprint 3	Sprint 3,frontend
Completed	closed	homebanking-demo	24	create bank branch	Not Available	5	Sprint 3	Sprint 3,frontend,managers
Completed	closed	homebanking-demo	25	create bank product	Not Available	5	Sprint 3	Sprint 3,frontend,managers
Completed	closed	homebanking-demo	26	add bank service	Not Available	5	Sprint 3	Sprint 3,frontend,managers
Completed	closed	homebanking-demo	28	assign employee to branch	Not Available	8	Sprint 3	Sprint 3,frontend,managers
Completed	closed	homebanking-demo	29	update interest rate	Not Available	3	Sprint 3	Sprint 3,frontend,managers
Completed	closed	homebanking-demo	20	send registration form	Not Available	5	Sprint 3	Sprint 3,frontend,public
Completed	closed	homebanking-demo	40	upload images frontend	Not Available	8	Sprint 4	Sprint 4,administration,frontend,managers
Remaining	open	homebanking-demo	23	sending email on registration request	New Issues	8	Sprint 4	Sprint 4,backend
Completed	closed	homebanking-demo	39	operation details	Not Available	5	Sprint 4	Sprint 4,customer,employee,frontend
Remaining	open	homebanking-demo	41	Documentation review	New Issues	15	Sprint 4	Sprint 4,documentation
Completed	closed	homebanking-demo	37	authorize operation	Not Available	3	Sprint 4	Sprint 4,employee,frontend
Completed	closed	homebanking-demo	38	negate operation	Not Available	3	Sprint 4	Sprint 4,employee,frontend

## Pivot Table_Github Issues_1
Milestone	Sum - Story Points
Sprint 1	34
Sprint 2	144
Sprint 3	103
Sprint 4	42
Total Result	323