## Intro
Sistema Home Banking
Report Scrum

Principi di Progettazione del Software a.a. 2018-2019
Università del Salento - Facoltà di Ingegneria dell’Informazione

Mirko Zizzari

## Product Backlog
		Nuove stime allo Sprint…
Voce	Stima iniziale dimensioni / (Story points)	1	2	3	4			Effort Totale / (Story Points)	Sprint 1	Sprint 2	Sprint 3	Sprint 4
Definire I requisiti e / l’architettura di alto livello (attori e casi d’uso)	20	5	0	0	0		Stimato	325	257	135	45	4			Story Points per Ora
Definire I requisiti di sistema	5	0	0	0	0		Ideale	325	243.75	162.5	81.25	0			2.03125
Progettazione del database	20	5	0	0	0
Configurazione Ambiente di Lavoro	10	2	0	0	0
Gestione Accessi	20	20	10	0	0
Testing	20	20	15	10	2
Come amministratore voglio / Creare il profilo delle banche del territorio	15	15	7	3	0
Come amministratore voglio / Definire le credenziali di un direttore per ogni banca	15	15	7	0	0
Come direttore voglio / Creare una o più filiali della mia banca	15	15	7	0	0
Come direttore voglio / Definire le credenziali dei cassieri per ogni filiale	15	15	7	0	0
Come direttore voglio / Creare un catalogo di / prodotti (conto corrente, carta prepagata) / e servizi (ricarica cellulare, pagamento bollo auto)	20	20	10	0	0
Il sistema applica periodicamente / gli interessi sui prodotti (conto e carta prepagata) / Con una percentuale definita dal direttore di banca. / Rispettando gli automatismi per operazioni dispositive	10	10	10	10	0
Come cassiere voglio / Prendere visione delle operazioni dei clienti / Potendole filtrare ed esportare	25	25	13	5	0
Come cassiere devo / Autorizzare o negare le operazioni dispositive	20	20	10	5	0
Come cliente della filiale voglio / Eseguire operazioni informative	15	15	7	3	0
Come cliente della filiale voglio / Eseguire operazioni dispositive	15	15	10	5	0
Come cliente voglio / Usufrire dei servizi offerti / (ricariche cellulare, pagamento bollo auto)	20	20	10	2	0
Un utente generico può / Prendere visione dei servizi offerti dal sistema, / Delle banche, ecc.	10	10	5	0	0
Un utente generico può / Richiedere la registrazione all’amministratore / Specificando banca e filiale	10	10	7	2	2
Documentazione	25	10	10	10	2
Burndown Chart
Story Points
Ore

## Github Issues
State	Issue Number	Issue Title	Story Points	Milestone	Labels
closed	4	Create MySQL Tables	3	Sprint 1	Sprint 1,backend,enhancement
closed	1	requirements and use cases	13	Sprint 1	Sprint 1,enhancement
closed	2	Database design	13	Sprint 1	Sprint 1,enhancement
closed	3	configurations for environment and builds	5	Sprint 1	Sprint 1,enhancement
closed	6	BankManager dashboard	13	Sprint 2	Sprint 2,backend
closed	7	employee dashboard	21	Sprint 2	Sprint 2,backend
closed	8	customer dashboard	21	Sprint 2	Sprint 2,backend
closed	9	visitor	13	Sprint 2	Sprint 2,backend
closed	15	upload images	8	Sprint 2	Sprint 2,backend
closed	16	export in pdf	8	Sprint 2	Sprint 2,backend
closed	17	retrieve images	5	Sprint 2	Sprint 2,backend
closed	5	Admin Dashboard	13	Sprint 2	Sprint 2,backend,enhancement
closed	10	implement spring security	13	Sprint 2	Sprint 2,backend,enhancement,security
closed	11	retrieve users info for web services	8	Sprint 2	Sprint 2,backend,enhancement,security
closed	14	operation filters	21	Sprint 2	Sprint 2,backend,jpa
closed	21	create bank	5	Sprint 3	Sprint 3,administration,frontend
closed	22	authorize registration request	5	Sprint 3	Sprint 3,administration,frontend
closed	27	automation of interests rate on products	8	Sprint 3	Sprint 3,backend,business
closed	18	login	8	Sprint 3	Sprint 3,backend,frontend
closed	30	deposit operation	5	Sprint 3	Sprint 3,customer,frontend
closed	31	withdraw operation	5	Sprint 3	Sprint 3,customer,frontend
closed	32	refill operation	5	Sprint 3	Sprint 3,customer,frontend
closed	33	transfer operation	8	Sprint 3	Sprint 3,customer,frontend
closed	34	car tax	5	Sprint 3	Sprint 3,customer,frontend
closed	35	customer list operation	5	Sprint 3	Sprint 3,customer,frontend
closed	36	employee list operations	8	Sprint 3	Sprint 3,employee,frontend
closed	19	home page with banks informations	5	Sprint 3	Sprint 3,frontend
closed	24	create bank branch	5	Sprint 3	Sprint 3,frontend,managers
closed	25	create bank product	5	Sprint 3	Sprint 3,frontend,managers
closed	26	add bank service	5	Sprint 3	Sprint 3,frontend,managers
closed	28	assign employee to branch	8	Sprint 3	Sprint 3,frontend,managers
closed	29	update interest rate	3	Sprint 3	Sprint 3,frontend,managers
closed	20	send registration form	5	Sprint 3	Sprint 3,frontend,public
closed	40	upload images frontend	8	Sprint 4	Sprint 4,administration,frontend,managers
open	23	sending email on registration request	8	Sprint 4	Sprint 4,backend
closed	39	operation details	5	Sprint 4	Sprint 4,customer,employee,frontend
open	41	Documentation review	15	Sprint 4	Sprint 4,documentation
closed	37	authorize operation	3	Sprint 4	Sprint 4,employee,frontend
closed	38	negate operation	3	Sprint 4	Sprint 4,employee,frontend
Sprints Effort (Github issues)
Story Points

## Pivot Table_Github Issues_1
Milestone	Sum - Story Points
Sprint 1	34
Sprint 2	144
Sprint 3	103
Sprint 4	42
Total Result	323